## 1. Product Overview
Item | Description
Product Name | MoneyMate
Product Vision / Purpose | To simplify shared expense management by enabling automatic bill splitting and instant settlements among students and young professionals.
Business Goals / Key Success Factors | • Reduce manual expense tracking effort by 80%
• Enable fast and secure settlements
• Provide clear analytics for group spending
• Achieve high user adoption through ease of use and clean UI
Primary Stakeholders | End Users (students, roommates, friends), Product Team, Developers, College Communities

## 2. Product Backlog
Epic ID | Epic Title | User Story ID | User Story/Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | Test Case (Tasks) | Test Owner
| Major features | Mandatory | Mandatory |  |  | (optional) | Mandatory | Mandatory | Mandatory | Mandatory
E1 | User Authentication | US1 | As a user, I want to sign up with email so that I can access my account securely. | Registration screen UI, Login screen | Must Have | 8 | To Do | Backend Dev Team | Validation+ login success | QA
|  | US2 | As a user, I want to receive error messages for wrong password so that I know what went wrong | error screen, | Must Have | 3 | To Do | Backend Dev | Wrong password | QA
|  | US7 | As a user, I want my session to be saved so I don’t need to log in every time. | storage, Auto-login logic | Should Have | 5 | In Progress | Backend Dev | Session persistence test | QA
E2 | Dashboard | US5 | As a user, I want to view analytics on a dashboard so that I can see trends quickly. | Dashboard UI, Graph components, API integration | Should Have | 13 | In Progress | Frontend Dev | Analytics display test | QA
|  | US6 | As a user, I want to see my recent expenses for better tracking. | Recent transaction list, Sync with database | Could Have | 8 | To Do | Frontend Dev | Recent list test | QA
|  | US3 | As a user, I want to view my monthly budget summary for better control. | Budget summary card UI, DB fetch | Must Have | 5 | To Do | Frontend Dev | Budget summary test | QA
E3 | Groups | US8 | Create group for shared expenses | Group table + UI form | Must Have | 8 | To Do | Full-Stack Dev | Group creation test | QA
|  | US9 | Add / remove group members | Permission & update APIs | Must Have | 5 | To Do | Backend Dev | Member update test | QA
|  | US10 | View group-wise expense summary | Aggregation query + cards | Should Have | 8 | In Progress | Frontend Dev | Summary comparison test | QA
|  | US11 | Split bills automatically among group members | Calculation logic + UI | Must Have | 13 | To Do | Backend Dev | Split correctness test | QA
E4 | Personal Expenses | US12 | Add personal expense manually | Input form + DB insert | Must Have | 5 | In Progress | Frontend Dev | Add expense test | QA
|  | US13 | Upload receipt images | File upload + parsing | Should Have | 8 | Planned | Backend Dev | Upload test | QA
|  | US14 | Categorize expenses | Tagging + category mapping | Must Have | 5 | To Do | Backend Dev | Category mapping test | QA
|  | US15 | View monthly expense graph | Chart UI + DB fetch | Should Have | 8 | To Do | Frontend Dev | Graph render | QA
Notes: | MoSCoW
|  | Must Have | Critical requirements that are essential for the project's success and must be delivered.
|  | Should Have | Important requirements that are highly desirable but not vital; the project can still be delivered without them, but it would be less ideal.
|  | Could Have | "Nice-to-have" requirements that are less important and have a lower impact if they are not included.
|  | Won't Have | Requirements that are not being delivered in the current project or timeframe, but may be considered for future iterations.
Story Points
|  | Fibonacci | 0,1,1,2,3,5,8,13,21,34,….
|  | (Modified) | 0,1,1,2,3,5,8,13,20 (points decided based on a User Story's complexity, effort needed & riks)
Ends at 20. Rarely extended to 40 and 100 for very large tasks.

## 3. Roadmap
Release | Target Date | Key Features | Dependencies | Demo Status
Llist Epic Names
v0.1 | 2025-11-15 | Auth + Dashboard MVP | None | Done
v0.2 | 2025-11-22 | Analytics + Notifications | API Upgrade | Done
v0.3 | 2025-11-29 | Group Creation | — | Done
v0.4 | 2025-12-06 | Expense Upload | OCR API | Done
v0.5 | 2025-12-13 | Expense Analysis | Base44 | In Progress
v1.0 | 2025-12-20 | History + Insights | Backend Sync | Planned
v1.1 | 2025-12-27 | Budget Alerts (AI) | None | Planned

## 4. Retrospective
Note: This is for the team to learn and improve. I have taught you in the class on Nov 4, 2025.
Ideally, the team should do this at the end of every release. How often you do , I leave it to you.
What Went Well | What Didn’t Go Well | Improvements / Action Items | Owner
Net time what will you do differently
Team collaboration was great | Test coverage was low | Automate test pipeline in next sprint | Test Lead
Requirement clarity improved | Some tasks lacked estimation | Conduct estimation workshop | Scrum Master
Good communication between frontend & backend | Delay in integrating notifications | Define integration checkpoints | Dev Team
Dashboard design finalized quickly | Time taken for flow debugging | Improve debugging workflow | Backend Dev